## Phases
Phase | Sub-tasks | Responsible Party
Contract | Signed Contracts Received:
| Medisolv Subscription Service Agreement | Organization
| Medisolv Data Authorization | Organization
| Organization BAA | Organization
| Kick-off Call | Medisolv
Install | Organizational Profile and End-Users Received by Medisolv | Organization:
| Application Installed by Engineering | Medisolv
| Base configuration completed (Document:Measure Selection Form) | Medisolv/Organization
| End Users Added | Medisolv
| Client Services Validation | Medisolv
Data Intake | Data Intake Contact with Facility Technical Contact | Medisolv - Organization Contact:
| sFTP established | Medisolv/Organization
| Technical Contact Sends Test Files | Organization
| Validation #1 Data Intake Sign-off | Medisolv
| Validation #2 Medisolv Client Services Sign-off | Medisolv
Training | ENCOR Abstractor Training | Medisolv/Abstractors
| ENCOR Abstracted Administrator Training | Medisolv/Facility Administrators (Role in ENCOR Abstracted)
| ENCOR Abstracted Presubmissions Training | Medisolv/Facility Administrators (Role in ENCOR Abstracted)
| ENCOR Abstracted Report and ENCOR Dashboard Training | Medisolv/Organization
Maintenance | Continued Support | Medisolv
| Webinars | Medisolv
| Medisolv Knowledge Center | Medisolv
| Submissions | Medisolv

## Tasks
Tasks | Target Deadline | Completion Date | Responsible
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Facility Go Live
Facility:
Go Live:
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Client Services Contacts
Implementation Lead:
Primary Advisor:
Secondary Advisor:
Client Services: encorsupport@medisolv.com
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Kick Off Call
Kick Off Call Completed |  |  | Medisolv-Implementation Lead
Measure Selection Form Sent |  |  | Medisolv-Implementation Lead
Data Intake Introductory Email Sent |  |  | Medisolv-Data Intake
SFTP Introductory Email Sent |  |  | Medisolv-Network Security
Step 1 Validation Completion - TP Update |  |  | Primary Advisor Task
Medisolv Sign Off |  | Hospital Sign Off
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Registration
Registration Invites Sent |  |  | Medisolv-Implementation Lead
Mass Email Registration Invite Sent |  |  | Medisolv-Implementation Lead
Registration Updates: Review of End Users |  |  | Medisolv-Implementation Lead
End User Registration Completed |  |  | Hospital
Medisolv Sign Off |  | Hospital Sign Off
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Measure Selection Form
Completed Measure Selection Form |  |  | Hospital
Measure Selection Review |  |  | Medisolv Primary Advisor
Medisolv Sign Off |  | Hospital Sign Off
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
ENCOR-a Process Set Up
GWTG Set Up |  |  | Implementation Lead
Enabled Measures |  |  | Medisolv Primary Advisor
Entered Expected IPP |  |  | Medisolv Primary Advisor
Sampling Set Up |  |  | Medisolv Primary Advisor
Medisolv Sign Off |  | Hospital Sign Off
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Data Validations
Test Files Sent |  |  | Hospital
Test Files Signed Off |  |  | Medisolv Data Intake
File Processing Notifications Set Up |  |  | Medisolv Primary Advisor
Production Data Sent |  |  | Medisolv Data Intake
Step 3 Production Data Validated |  |  | Medisolv Primary Advisor
Medisolv Sign Off |  | Hospital Sign Off
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
ENCOR-a Overviews
New/Edit/Remove End User Process |  |  | Medisolv Primary Advisor
End User List and End User Audit Trail |  |  | Medisolv Primary Advisor
Invalid Import Results/Import Encor Summary Overview |  |  | Medisolv Primary Advisor
Knowledge Center Overview |  |  | Medisolv Primary Advisor
Case History/Patient Population/Quarterly Population & Sampling Reports |  |  | Medisolv Primary Advisor
Sampling and Mark Period Ready for Abstraction Overview
Medisolv Sign Off |  | Hospital Sign Off
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Vendor Authorizations
CMS/TJC Vendor Authorization Process Overview |  |  | Medisolv Primary Advisor
CMS Vendor Authorization Info Sent |  |  | Implementation Lead
CMS Vendor Authorization Completed |  |  | Hospital
TJC Submission Selections Completed |  |  | Hospital
TJC Vendor Authorization Info Sent |  |  | Implementation Lead
TJC Vendor Authorization Granted |  |  | Hospital
Medisolv Sign Off |  | Hospital Sign Off
ENCOR for Hospital Abstracted Measures Training(s)
Medisolv Sign Off Column1: Abstractor Training | Laurie steps away at Abstractor Training, Primary Advisor leading going forward.

## Data Intake
Deadline Date | Task | Details | Completion Date | Medisolv Sign Off | Hospital Sign Off
Week of : | Column1 | Column2 | Column3 | Column4 | Column5
Week of : | Test File Builds | If additional assistance is needed from the Medisolv Data Intake team, a meeting can be set up.
Week of : | Submit Round 1 Test Files | Hospital IS Team to place Test Files on server for Medisolv to pick up
Week of : | Review/Correct Round 1 Test files | Hospital IS Team to review corrections of Test files sent from the Medisolv Data Intake team and make corrections as recommended by the Medisolv Data Intake team
Week of : | Submit Round 2 Test Files | Hospital to place Test Files on server for Medisolv to pick up
Week of : | Review/Correct Round 2 Test files | Hospital IS Team to review corrections of Test files sent from the Medisolv Data Intake team and make corrections as recommended by the Medisolv Data Intake team
Week of : | Submit Round 3 Test files (additional rounds may be added as needed) | Hospital IS Team to place Test Files on server for Medisolv to pick up
DATA INTAKE Sign Off

## Weekly Notes
Primary Advisor:
Secondary Advisor:
Implementation Lead: Laurie Powers
Progress Update Date: | Attendees: | Progress Update Notes:

## After Go Live-PCQA
After Go Live Tasks | Notes
Remove Previous Vendor - CMS | Primary Advisor, mark your calendar to reach out to client once the IP Clinical File CMS Deadline date is completed.
Project Implementation Acknowledgement Form | The Form must be completed once training is complete and returned to Brian Hill.
Reports and Dashboard Training | Primary Advisor, update the TP with the R/D training completion date. Tag Brian Hill in the TP so he may close it.
Administrator Training | Primary Advisor, update the TP with the Administrator training completion date.
Pre Submission Checks and Submission Overview | Primary Advisor, update the TP with the Pre-Submission Overview completion date.